## Thornborough
[6 empty] | Evaluation Scoring: See tab 'Scoring Criteria' for details | [10 empty] | Objective | Weighting
Buckinghamshire Section 19 Investigations | [5 empty] | -2 | Major negative impact. | [9 empty] | 1 | 1
Multi-Criteria Appraisal Matrix | [5 empty] | -1 | [10 empty] | 2 | 1
[6 empty] | 0 | Neither positive or negative impacts | [9 empty] | 3 | 1
[6 empty] | 1 | [10 empty] | 4 | 1
Originated | Seraya Sigsworth | 2021-10-12 |  |  |  | 2 | [10 empty] | 5 | 1
Checked | Anna Beasley | 2022-05-19 |  |  |  | 3 | [10 empty] | 6 | 1
Approver | Anna Beasley | 2022-05-19 |  |  |  | 4 | [10 empty] | 7 | 1
[6 empty] | 5 | Major positive impact | [9 empty] | 8 | 1
[17 empty] | 9 | 1
[17 empty] | 10 | 0
[17 empty] | 11 | 0
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Reference | Opportunities | Lead RMA | Flood risk benefit to property | Flood impact on people | Data and evidence | Deliverability | Community/ resident acceptability | Biodiversity and water quality betterment | Amenity benefits | Carbon reduction | Maintenance costs | Timescale | Cost (for information only) |  |  | TOTAL
1 | Do nothing | N/A | -1 | -1 | 0 | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 5 | -2 | 5 | -3
2 | Business as usual | All | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 |  |  | -1
Options
3 | Investigate opportunities for installing PFR at relevant at-risk properties | Homeowners | 1 | 4 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 3 | 5 | -2 | 5 | 8
4 | Create a community Flood Action Plan to formalise any existing arrangements | Community / Flood Action Group | 1 | 3 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 5 | 5 |  |  | 8
5 | Prepare a “flood preparedness” information pack for existing and future residents | Community / Flood Action Group | 1 | 3 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 5 | 5 |  |  | 8
6 | Work towards procuring a Community Flood Toolkit for Thornborough | Community / Flood Action Group, Buckinghamshire Council, Environment Agency | 1 | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 4 | 5 |  |  | 9
7 | Increase frequency of highway gully maintenance | Transport for Buckinghamshire | 1 | 3 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 4 | 5 |  |  | 7
8 | Engagement with landowners/farmers to explore potential for NFM/land management e.g water storage, ditches, buffer strips/headgerows etc | Flood Action Group and Land Owners, supported by Buckinghamshire Council (LLFA) | 1 | 4 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 3 | 5 |  |  | 8
9 | Watercourse maintenance plan and riparian awareness (to include activities required, frequency etc) | Riparian owners, with support from Parish Council and Buckinghamshire Council | 1 | 3 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 4 | 5 |  |  | 6
10 | Complete appraisal for future management of the weir at Thornborough Mill and disseminate findings | Environment Agency | 1 | 2 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 5 | 4 |  |  | 11
11 | Regular inspection of all bridges and culverts to prevent blockages | Riparian owners, IDB, TfB | 1 | 3 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 4 | 5 |  |  | 6
12 | Removal of livestock gate at Hatchet Leys Lane | Riparian owner/Farmer | 1 | 3 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 5 | 5 |  |  | 7
13 | Investigate feasibility of bypass route at Hatchet Leys Lane | Buckinghamshire Council | 1 | 4 | 0 | -1 | 1 | 0 | 0 | 0 | 0 | 3 | 5 |  |  | 5

## SCORING CRITERIA (2)
1 | Contribute towards reducing flood risk to property | Likely change in internal flood risk to property |  | Aligns with OM1A - economic damages
|  | -2 | Increase in flood risk to any property
|  | -1 | N/A
|  | 0 | No perceived change
|  | 1 | Reduction in flood risk to 1 - 10 properties
|  | 2 | Reduction in flood risk to 10 - 30 properties
|  | 3 | Reduction in flood risk to 30 - 70 properties
|  | 4 | Reduction in flood risk to 70-100 properties
|  | 5 | Reduction in flood risk to >100 properties
2 | Contribute towards reducing flood impacts on people/communities | Likely change in flood impacts on people/communities. Encompassing community preparedness and resilience; stress, health, mental health impacts; nuisance flooding (gardens, roads etc); disruption to access and egress; vehicle damages; risk to life and evacuation costs. |  | Aligns with OM1B - people related benefits - risk to life, mental health, vehicle damages, evacuation costs
|  | -2 | Major negative change in flood impacts on people/communities
|  | -1 | Minor negative change in flood impacts on people/communities
|  | 0 | No perceived change
|  | 1 | Minimal positive change in flood impacts on people/communities (e.g. reduction in nuisance flooding)
|  | 2 | Minor positive change in flood impacts on people/communities (e.g. reduction in disruption to toilet use)
|  | 3 | Minor positive change in flood impacts on people/communities (e.g. improvements to access and egress)
|  | 4 | Medium positive change in flood impacts on people/communities (e.g. increasing community flood preparedness and ability to act)
|  | 5 | Major positive change in flood impacts on people/communities (e.g. reduction of risk to life and evacuation costs)
3 | Contribute to improving the availability of data, evidence and modelling to support option development or flood incident response | This criteria focusses on the benefits of further data collection and evidence studies to support option development
|  | 0 | Does not improve the availability of data, evidence and modelling
1
|  | 2 | Will provide additional data, evidence or modelling, helpful in development of interventions
3
4
|  | 5 | Improvement to data, evidence and modelling which is essential to the development of a capital scheme
4 | Deliverability | Likely deliverability of the intervention considering construction complexity, access, designations, services, space, land ownership, available materials and expert equipment or advice required.
|  | -2 | Deliverability is at high risk of complexity/constraints
-1
|  | 0 | Not known/not applicable
1
|  | 2 | Deliverability is at low risk of complexity/constraints
5 | Community / resident acceptability | Community buy in or perceived residents opinion.
|  | -2 | Community/residents are likely to have objections
|  | -1 | Community/residents may not be receptive
|  | 0 | No known objections / constraints
|  | 1 | Community/residents are likely to be receptive but may have some constraints
|  | 2 | Community/residents are likely to be receptive and have no constraints
6 | Contribute towards biodiversity and water quality betterment | Potential for the intervention to provide creation of habitats and river restoration, as well as improving existing water quality.
|  | -2 | Significant detriment
|  | -1 | Some detriment
|  | 0 | No perceived change
|  | 1 | Some betterment
|  | 2 | Significant betterment
7 | Contribute towards amenity benefits | Potential for the intervention to improve the amenity value of the surrounding area.
|  | -2 | Significant detriment
|  | -1 | Some detriment
|  | 0 | No perceived change
|  | 1 | Some betterment
|  | 2 | Significant betterment
8 | Contribute to carbon reduction | Potential for the intervention to contribute towards carbon reduction via sustainable construction techniques or carbon sequestration from increased planting.
|  | -2 | Significant net carbon increase
|  | -1 | Some net carbon increase
|  | 0 | Not known/no effect
|  | 1 | Some net carbon reduction
|  | 2 | Significant net carbon reduction
9 | Maintenance | High level assessment of maintenance requirements.
|  | -2 | N/A
|  | -1 | High cost/frequency maintenance, requires new and specialised maintenance routines
|  | 0 | Not known/no effect
|  | 1 | Low-cost maintenance, can be compelted as part of existing maintenance routines
|  | 2 | No active maintenance required (passive maintenance designed)
10 | Timescale | 1 | Long term strategic aim (>10yrs to progress, funding route unclear)
2
|  | 3 | Likely to be able to progress in next 1 - 5 yrs e.g. through FCERM partnership funding programme
4
|  | 5 | Quick win (<1yr), BC able to fund directly
11 | Cost | High level assessment of cost of implementing |  | For information only, not included in total
|  | 1 | £>2m
|  | 2 | £1m to 2m
|  | 3 | £500k-£1m
|  | 4 | £100-500k
|  | 5 | <£100k